## Ark1
Good Food Mood | PLANNING & RESEARCH |  |  |  |  | SKETCHING, MOCK-UP & DRAFTING |  |  |  |  | BUILD & CODE |  |  |  |  | DESIGN |  |  |  |  | REVIEW & VALIDATE
Start-up date: 14.07.21
End date: 22.08.21 | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14 | DAY 15 | DAY 16 | DAY 17 | DAY 18 | DAY 19 | DAY 20 | DAY 21 | DAY 22 | DAY 23 | DAY 24 | DAY 25
FREDRIK ERIKSEN | PROJECT/ASSIGNMENT WORK |  |  |  |  | PROJECT/ASSIGNMENT WORK |  |  |  |  | PROJECT/ASSIGNMENT WORK |  |  |  |  | PROJECT/ASSIGNMENT WORK |  |  |  |  | CODE REVIEW AND OPTIMIZATION
READ THROUGH ASSIGNMENT Get a good understanding and overview (2 hours)
STRATEGIC PLANNING Decide and prioritize all the tasks and make Gantt Chart (3 hours)
RESEARCH DETERMINE STRATEGY Research similar webpages (6 hours)
CREATE STYLE TILES & CHOOSE URL NAME (8 hours)
DRAW SKETCHES ON PAPER AND BRAINSTORM IDEAS FOR LAYOUT Draw ideas for the microsite layout and what to inculde. (2 hours)
CREATE MOCK-UPS FOR THE SITE. DIGITAL WIREFRAME/BREAKPOINTS Make sure content is displayed in a good way on all devices. Set pixel breakpoints for reference. (6 hours)
JAVASCRIPT, HTML & CSS CODING Start building code for the page. Considering good wireframe, SEO, WCAG etc. (30 hours)
SITE BUILD & API INTEGRATION Test code, commit to GitHub, run scripts, implement API. (18 hours)
MAKE UX/UI FRIENDLY Review content and consider user interference/experience. (8 hours)
DESIGN ELEMENTS AND PAGE CONTENT Make design fluid with responsive page (10 hours)
DESIGN IDENTITY ELEMENTS (6 hours)
IMAGES AND MEDIA Find images to use, and place them into a good layout on the page.
UX/UI TESTING (1 hours)
CROSS DEVICE, PLATFORM & BROWSER TESTING (2 hours)
[23 empty] | VALIDATE (0.5 hours) | ADJUSTMENTS LAST REFINEMENT (2 hours)
DELIVERY/ SUBMISSION (0.5 hours)